## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 1 | 4 | 2 | 20 | Team Lead and all members | 2022-09-26 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class | Closed
| add new team members | One or more classmates join our team | 1 | 3 | 2 | 30 | Team Lead and all members | 2022-09-26 | Reassign tasks from current members to the new member(s) | Jintong joined the team after Iteration 0 presentation and has since worked to get up to speed on the tech stack | Closed
| Lack of motivation or responsibility | One or more team members do not complete all of their tasks to an appropriate standard in agreed upon timeframes | 2 | 3 | 3 | 36 | Team Lead and all members | 2022-12-09 | Identify root cause of unmotivation and discuss countermeasures | No issues identified so far | Open
Communication | duplicate work | Two or more team members mistakenly work on the same task | 3 | 2 | 2 | 24 | All Members | 2022-12-09 | Review both works and come to a consensus on which one to use, improve visibility of task assignments | No duplication so far | Open
| worked on wrong components | Team member works on a task assigned to other team member | 3 | 3 | 2 | 18 | All Members | 2022-12-09 | Improve visibility of task assignments | No duplication so far | Open
| useless work | Team member works on task not necessary for project | 1 | 3 | 3 | 45 | All Members | 2022-12-09 | Improve visibility of task assignments | No useless work so far | Open
Requirements | unclear requirements | Team member confused about the requirements of a component | 3 | 3 | 3 | 27 | Requirements Lead | 2022-10-28 | Improve explanation of the requirements | No confusion identified yet | Open
| scope creep | Scope of the project keeps increasing | 3 | 2 | 3 | 36 | Requirements Lead | 2022-10-28 | Set firm date to finalize project scope | No creep yet | Open
| constant requirements changes | Requirements change in priority or quantity | 1 | 2 | 3 | 60 | Requirements Lead | 2022-10-28 | Set firm date to finalize requirements | No requirement changes yet | Open
Management | improper task assignments | Team lead assigns tasks incorrectly | 2 | 2 | 4 | 64 | Team Lead | 2022-12-09 | Team Lead coordinates with other team members to ensure correct assignments going forward | No improper task assignments yet | Open
| improper planning | Team lead fails to plan meetings or assignments | 2 | 2 | 4 | 64 | Team Lead | 2022-12-09 | Team Lead prepares for meetings more ahead of time | No issues identified so far | Open
| lack of management skills | Team lead unable to manage teammates effectively | 2 | 3 | 3 | 36 | Team Lead | 2022-12-09 | Team Lead works on how he communicates with other team members | No management issues identified yet | Open
Technology competence | Not familiar with the framework used | One or more team members are unfamiliar with the framework used | 5 | 3 | 3 | 9 | All Members | 2022-10-28 | Team members will work on improving framework knowledge and skills through tutorials and practice | Team members have continued to watch tutorials and work through examples to develop the skills necessary to understand the project | Open
| Not familiar with the programming language used | One or more team members are unfamiliar with the language used | 2 | 4 | 3 | 24 | All Members | 2022-10-28 | Team members will practice and use tutorials as necessary | No issues identified so far | Open
| Not familiar with unit testing | One or more team members are unfamiliar with unit testing | 4 | 3 | 3 | 18 | All Members | 2022-10-28 | Team members will go through tutorials and members more familiar with unit testing will assist those less familiar | No issues identified so far | Open
| Other technology incompetence | One or more team members are unfamiliar with another required technology | 3 | 2 | 3 | 36 | All Members | 2022-11-18 | Team members will familiarize themselves with the other technology using tutorials | Team members were provided with appropiate tutorials to review and have asked questions as they came up | Open
| Not familiar with Git | One or more team members are unfamiliar with Git | 3 | 2 | 2 | 24 | All Members | 2022-09-26 | Team members will go through git tutorials | Team members were provided with git tutorials to review and have asked questions as they came up | Closed
Design and implementation | Improper design | The application is improperly designed | 2 | 4 | 2 | 16 | Design Lead | 2022-10-28 | Appropriate design will be determined and extra work will be assigned to catch the project up | No issues identified so far | Open
| improper technology stack | The wrong technology stack is chosen | 2 | 4 | 2 | 16 | Design Lead | 2022-10-28 | Appropriate stack will be identified and extra work will be assigned to catch the project up | No issues identified so far | Open
| Messy code | Code is written in a difficult to read manner | 3 | 2 | 3 | 36 | Design Lead | 2022-11-25 | Team members will be reminded of the coding standards and best practices agreed to | No issues identified so far | Open
Testing | Not enough testing | Testing does not cover all likely use cases | 3 | 3 | 2 | 18 | QA Lead | 2022-11-18 | Add more testing to improve coverage | No issues identified so far | Open
Integration and deployment | Not enough time for integration and deployment | By the time the app is completed, there is no time to finalize the deployment | 3 | 2 | 4 | 48 | Configuration Lead | 2022-11-25 | Begin the deployment development process earlier | No issues identified so far | Open